ENG-06

ECO Impact Analyzer

Design Specification

Aerospace & Defense Electronics

Joins ECO content to inventory state and IMS schedule data to surface orphan exposure and slip risk before CRB approval.

Version 0.1 — Draft for Review

April 2026

# Table of Contents

# 1. Executive Summary

ENG-06 is a Mendix Marketplace application that gives Change Review Boards a CRB-ready impact assessment of any proposed or in-flight Engineering Change Order in minutes, not days. It joins the ECO's content (added, removed, and revised parts; affected drawings; effectivity) against two domains the ECO usually doesn't touch directly: the inventory and demand graph (the same data lake that powers SCM-05) and the Integrated Master Schedule (Deltek Cobra and Microsoft Project / Project Server). The output is two ranked tables — orphaned-inventory exposure with mitigation, and IMS schedule-slip risk with factor attribution — plus a Guided Copilot for natural-language Q&A over the joint impact.

ENG-06 is paired with two existing portfolio apps. ENG-02 Engineering Change Drafting Assistant helps engineers author a clean ECO; ENG-06 helps the program vet the resulting ECO before the CRB approves it. SCM-05 Multi-Level Pegging Explorer provides the BOM-closure and supply/demand graph; ENG-06 reuses those entities directly rather than reproducing them.

Two questions this app answers 1. What inventory does this ECO orphan? Fully, partially, with what dollar exposure, and what should we do about it? 2. What does this ECO slip in the schedule? Per program, per customer milestone, with factor attribution we can defend in a CRB.

# 2. Business Context

## 2.1 Why CRBs miss things

An Engineering Change Order's downstream effects are spread across systems that don't share a current-state view. PLM owns the change content; ERP owns inventory and demand; the IMS owns the schedule. Today, CRB packages reconcile these by hand: a planner walks each affected part for orphan exposure, a scheduler walks the IMS for slip risk, and the PowerPoint that lands on the CRB chair's desk is one to three days behind the actual change. Late-discovered orphan inventory and missed schedule slips are the most common forms of bad news that surface after CRB approval.

## 2.2 What ENG-06 changes

- Impact assessment is computed from current data on every load — not snapshotted into a slide deck.

- Orphan classification distinguishes full from partial, with dollar exposure and a per-row mitigation chip (use-up-before-effectivity, transfer to spares/MRO, scrap, alternate-program allocation, hold, route to review).

- Schedule risk is scored against IMS data — Cobra activities and MS Project tasks — with factor attribution that survives CRB pushback.

- The Guided Copilot lets the CRB chair ask follow-ups in plain language and get cited tabular answers.

## 2.3 Personas

| Persona | Primary use | Permissions |
| --- | --- | --- |
| CRB Chair | Pre-meeting impact review; in-meeting Q&A; sign-off readiness check. | Read + comment |
| Program Manager | Per-program rollup; milestone-at-risk view; mitigation tracking. | Read + propose mitigation |
| Materials Manager | Orphan exposure ownership; mitigation execution (transfer to spares, scrap, etc.). | Read + assign mitigation |
| Component Engineer | ECO authoring (with ENG-02); pre-CRB validation in ENG-06; FFF-equivalence questions. | Read + propose ECO change |

# 3. Conceptual Model

## 3.1 Entities

ENG-06 reuses the SCM-05 entity model for parts, BOMs, supply, demand, and pegs. It adds the entities below for ECO content and impact findings:

| Entity | Key attributes |
| --- | --- |
| ECO | eco_id, change_kind {ECO¦ECR¦DCN¦TempDeviation¦Waiver¦FieldBulletin¦ServiceBulletin¦Other}, priority {Routine¦Urgent¦Emergency¦Mandatory¦Other}, status {Draft¦InReview¦PendingCRB¦Approved¦Rejected¦Withdrawn¦Implemented¦Closed}, issue_date, originator, affected_programs[], reason_for_change. |
| ECOItem | Composite child of ECO. action {Add¦Remove¦Revise¦ReviseQty¦Substitute¦MarkObsolete¦NoChangeButReKitting}, from_part, from_revision, to_part, to_revision, qty_per_change, qualification_impact_per_item. |
| Effectivity | kind {Date¦SerialNumber¦BlockNumber¦NextAssembly¦Lot¦ImmediateOnApproval¦Other}, literal_text. One-to-one with ECO. |
| AffectedDocument | identifier, from_revision, to_revision, change_description. References drawings, specs, ICDs, work-instructions affected by the change. |
| ImsScheduleReference | system_kind {Cobra¦MSProject¦P6¦OpenPlan¦Generic¦Unknown}, identifier, task_label. Pulled from the ECO body OR computed by the ENG-06 dependency walker. |
| OrphanedInventoryRow | part, classification {FullOrphan¦PartialOrphan¦NotOrphaned¦InsufficientData}, on_hand_qty, open_po_qty, remaining_demand_qty, orphaned_qty, unit_cost_usd, exposure_usd, mitigation_recommendation. |
| ScheduleImpactRow | ims_task, system_kind, program, score (0-100), factor_scores[5], recommended_action {NoAction¦Restage¦PartialEffectivity¦AddInventoryBuffer¦Defer¦RouteToReview}. |
| ImpactSnapshot | Audit row tying an ECO + as-of-date to the OrphanedInventoryRow and ScheduleImpactRow records that were produced. Append-only. |

# 4. Data Architecture

## 4.1 ECO ingest paths

ENG-06 supports three ingest paths, in order of preference:

- PLM pull (preferred). The framework subscribes to PLM ECO-state events from Teamcenter, Windchill, or Aras. On a relevant state change the runtime pulls the structured ECO + items + affected documents, normalizes them, and persists ECO and ECOItem rows directly. ENG-06-ECO-Extractor is invoked only on optional unstructured fields (free-text Reason for Change).

- Data-lake export. Some primes' ECOs land in the lake as a flattened key/value document (one row per ECO field, one per item). The framework reads from the lake, hydrates a synthetic eco_text payload, and runs ENG-06-ECO-Extractor against it. This path is well-suited to bulk historical loads.

- PDF / DOCX upload. Legacy ECO packages and supplier-issued field bulletins arrive as PDFs or Word docs. ENG-06-ECO-Extractor is the primary path. The framework injects page markers (<page n="<int>">) and form-field labels (where detectable) before invocation.

## 4.2 Inventory + IMS joins

The Mendix runtime queries the data lake for the inventory state (on-hand, open POs, demand by program) and the IMS state (Cobra activities and MS Project tasks). Both queries use the BOM closure cache from SCM-05 to compute remaining demand at the post-effectivity state.

| Source | Data captured | Refresh |
| --- | --- | --- |
| PLM (Teamcenter / Windchill / Aras) | ECO header, items, affected documents, qualification impact, approval state. | Event-driven on ECO state change. |
| ERP (Oracle EBS / SAP S/4 / IFS) | On-hand inventory, open POs, planned receipts, hard pegs, unit cost (PO line + standard cost). | CDC stream into lake; 1–5 min. |
| Data lake (Snowflake / Databricks) | BOM closure cache; consolidated demand; soft-peg ranker output (shared with SCM-05). | Materialized; refreshed by lake jobs. |
| Deltek Cobra (EVM + IMS) | Activity ID, task name, total float, critical-path flag, baseline finish, working finish, EVM status. | Daily snapshot + on-demand refresh. |
| MS Project / Project Server | Task ID, predecessor / successor edges, dates, custom fields for program / milestone tagging. | Daily snapshot + on-demand refresh. |
| Customer milestone calendar | Contract milestone IDs, baseline dates, customer-acceptance gates. | On change. |

## 4.3 Read-mostly with explicit write paths

ENG-06 is read-mostly. Two explicit write paths exist, both gated on approval:

- Mitigation assignment. A planner picks a mitigation chip on an OrphanedInventoryRow; ENG-06 records the choice locally, and surfaces it as a recommended action to the ERP / inventory team. It does not execute the scrap, transfer, or use-up itself.

- Schedule-action proposal. A program manager picks Restage / Add Buffer / Partial Effectivity on a ScheduleImpactRow; ENG-06 records it and emits a notification to the IMS owner. It does not edit Cobra or MS Project directly.

# 5. Orphan Analysis

## 5.1 Algorithm

For every part touched by the ECO, compute the post-effectivity remaining demand by walking the BOM closure forward from the to-state of the ECO. Compare against on-hand + open-PO inventory. Classify:

| Classification | Definition | Default chip |
| --- | --- | --- |
| FullOrphan | After effectivity, no remaining valid demand exists for this part anywhere in scope. | red |
| PartialOrphan | Remaining demand < (on-hand + open-PO qty); the surplus is the partial-orphan quantity. Exposure = surplus * unit cost. | amber |
| NotOrphaned | Remaining demand >= total committed supply; nothing surplus. | green |
| InsufficientData | Inventory or demand data missing; cannot classify. Always routes to a planner. | grey |

## 5.2 Exposure

Dollar exposure = orphaned_qty × unit_cost. The unit cost is taken from the most recent PO line on the part if one exists; otherwise from the ERP standard cost. The source is always cited — the framework requires it via RequireCitation with must_include_kind: unit_cost_source.

## 5.3 Mitigation options

- UseUpBeforeEffectivity — drain the surplus on builds before the ECO takes effect. Preferred when the effectivity is a serial / block range with sufficient runway.

- TransferToSparesOrMRO — reclassify the surplus as spares or sustainment inventory if the program supports it.

- ScrapAndWriteOff — last resort; quantified for finance.

- AlternateProgramAllocation — move the surplus to a different program where the part is still active.

- ReturnToSupplier — open POs may be cancellable or returnable depending on terms.

- Hold — defer decision; show the row in the queue with a follow-up date.

- RouteToReview — when ENG-06 cannot recommend confidently. Always available; default for safety-of-flight rows.

# 6. Schedule-Slip Risk Scoring

## 6.1 Scope

The schedule analyzer takes (a) the IMS task references the ECO already names, and (b) any task ENG-06 reaches by walking dependencies forward / backward through the IMS dependency graph. The framework limits the walk to a configurable depth (default: 3 hops upstream, 3 hops downstream from any ECO-named task).

## 6.2 Rubric

Each affected task gets a 0–100 score (higher = greater slip risk) computed from a weighted rubric. The rubric is declared on the ENG-06-Impact-Scorer template and versioned alongside it.

| Factor | Weight | Drivers |
| --- | --- | --- |
| Critical-path proximity | 30 | Task total float (days); is_on_critical_path; distance to critical path. |
| Qualification burden | 25 | qualification_summary level (FFF preserved → flight requalification); first-article required; customer concurrence required. |
| Long lead in new config | 20 | Max lead time of any newly-introduced part; single- vs dual-source posture on those parts. |
| Approval-path latency | 15 | Pending approval gates; customer concurrence; FAA / DCMA touchpoints. |
| Build-up inventory | 10 | Weeks needed to build a buffer of the to-part; current on-hand of the to-part. |

## 6.3 Recommended actions

- NoAction (under safety-of-flight floor: Restage)

- Restage — re-sequence the affected tasks to absorb the qualification or long-lead gap.

- PartialEffectivity — implement the ECO over a serial / block range that gives the program runway.

- AddInventoryBuffer — pre-build a buffer of the to-part to bridge the qualification gap.

- Defer — push effectivity to a later window.

- RouteToReview — when the model cannot recommend confidently. Floor for any task whose program end-item is safety-of-flight.

## 6.4 Program rollup

Per program: the maximum task score, the total orphan exposure, and the list of customer milestones whose forecast finish slips past the baseline. The rollup is what the CRB chair sees first.

# 7. AI Workflows

All three ENG-06 AI workflows ride on the AI Interaction Framework, with the same governance posture as SCM-05's three workflows.

## 7.1 ECO ingestion — Document-Extract

Template: ENG-06-ECO-Extractor v1.0.0. Document-Extract primitive (Wave 1, formalized). Status: Draft, ships in Wave 2 alongside ENG-06.

The PLM-pull path uses this template only on free-text fields. The data-lake and PDF/DOCX paths use it as the primary parser. The schema captures every fact a CRB needs and is the input contract for the ENG-06 impact engine.

## 7.2 Impact scoring — Decision Support & Triage

Template: ENG-06-Impact-Scorer v0.1.0-stub. DS&T primitive (Wave 3 — not yet formalized). Status: stub.

Two-pass output: orphan_findings (one row per affected part) and schedule_findings (one row per affected IMS task). Per-program rollups are computed from those rows. Every factor cites the input it came from; the framework's RequireCitation guardrail rejects any output missing the unit-cost source on an exposure row.

## 7.3 Impact Q&A — Guided Copilot

Template: ENG-06-Impact-Copilot v0.1.0-stub. Guided Copilot primitive (Wave 2 — not yet formalized). Status: stub.

Tool surface (a superset of the SCM-05 Copilot's):

load_eco(eco_id) -> EcoExtraction

joined_orphans(eco_id, as_of_date, program_scope) -> OrphanFinding[]

joined_schedule_impact(eco_id, as_of_date, program_scope) -> ScheduleFinding[]

where_used(part_id_or_mpn, as_of_date, include_obsolete) -> WhereUsedRow[]

explode_bom(parent_part_id, as_of_date, effectivity_filter) -> BomLineRow[]

ims_task_dependencies(task_id, system_kind, depth) -> ImsDependencyEdge[]

milestone_status(milestone_id) -> MilestoneStatus

The Copilot never edits ECO state, peg state, or IMS data. It is read-only. The framework's RefuseIfUngrounded guardrail rejects any answer that introduces a fact the tools did not return.

# 8. UX Patterns

## 8.1 Three-pane layout

Top bar with program scope, lake refresh status, and IMS source identifiers. ECO header sub-bar with ECO ID, badges (priority, qualification, effectivity, ITAR), and a Proposed / Baseline / Δ Diff toggle. The body is three panels: ECO content on the left, joint impact (orphan + schedule) in the center, and the Impact Copilot on the right.

## 8.2 Color and chip conventions

- ECO action chips: ADD (green), REMOVE (red), REVISE (blue), SUBSTITUTE (amber).

- Orphan classification dots: red full, amber partial, green none, grey insufficient-data.

- Schedule score: a 0–100 ring with red / amber / green hue tied to the score band; factor bars show contribution.

- Program rollup chip: high / med / low based on the maximum task score and total exposure.

# 9. Governance & Compliance

- DataSensitivityTier = ITAR on every ENG-06 template. Only Bedrock_Claude (GovCloud) and OnPremGateway backends are allowed.

- Role scoping: out-of-scope programs are invisible — including in the AI panel. The Copilot refuses with refusal_reason = out_of_role_scope on any cross-scope question.

- No autonomous actions: ENG-06 can propose mitigations and schedule actions but cannot execute them. The ERP and IMS remain authoritative.

- Audit: every ImpactSnapshot is append-only. Every Copilot answer's tool invocations and returned IDs are recorded so a 2030 reviewer can replay the same call.

- Safety-of-flight: any task whose end item is_safety_of_flight = true cannot receive a NoAction recommendation. Floor is RouteToReview.

# 10. Roadmap

## 10.1 Wave 2 — Initial release

- Mendix module v1.0.0 with PLM ingest (Teamcenter + Windchill), data-lake export ingest, PDF/DOCX upload.

- ENG-06-ECO-Extractor template published (Document-Extract is formalized).

- ENG-06-Impact-Copilot template published when the Wave 2 Guided Copilot primitive ships.

- Reference integrations: Cobra, MS Project; Snowflake reference lake.

## 10.2 Wave 3 — Triage and depth

- ENG-06-Impact-Scorer template published when the Decision Support & Triage primitive ships.

- Drafting & Generation primitive lights up the CRB Memo Draft button (auto-drafts the impact memo from the ImpactSnapshot, with reviewer queue).

- Aras PLM and Primavera P6 integrations as additional reference adapters.

- ECO outcome learning: post-implementation reconciliation of forecast vs actual slip / orphan reality, surfaced as a private model-evaluation signal.

# 11. Glossary

| Term | Definition |
| --- | --- |
| A&D | Aerospace & Defense. |
| BOM | Bill of Materials. |
| CRB | Change Review Board / Configuration Review Board. |
| DCN | Drawing Change Notice. |
| ECO / ECR | Engineering Change Order / Request. |
| ERP | Enterprise Resource Planning system. |
| EVM | Earned Value Management. |
| FFF | Form, Fit, and Function — the equivalence test for a replacement. |
| IMS | Integrated Master Schedule. |
| LRU | Line-Replaceable Unit. |
| MES | Manufacturing Execution System. |
| MPN | Manufacturer Part Number. |
| MRO | Maintenance, Repair, and Overhaul. |
| PCN | Product Change Notice. |
| PLM | Product Lifecycle Management (Teamcenter, Windchill, Aras). |
| TF | Total Float — schedule slack on a task. |
| WBS | Work Breakdown Structure. |